## Sheet1
S.no | Tasks | Deadline | Status | Comments | Implementer
Code
Teensy
1 | Upload Teensy working code | 2023-03-07 | Done | This code should be working as of Feb 2023 | Kaushik
2 | Write description for Teesny code | 2023-03-07 | In Progress | Reorganizing the working code and writing description | Kaushik
3 | Teensy Code Flow chart | 2023-03-07 | In Progress | Working on the flow chart | Kaushik
4 | Check Stop and End stop conditions | 2023-03-07
5 | Remove Unused Functions | 2023-03-08
6 | Code Review | 2023-03-08
Raspberry pi
7 | Display motion rate increase | 2023-03-09
8 | Data collection Cloud upload | 2023-03-09
9 | Pressure increase problem | 2023-03-09
10 | Change pressure bar GUI | 2023-03-09
11 | Date Auto Update | 2023-03-09
Hardware/Electronics
12 | Solve Motor controller Serial problem (Jitter)
13 | Move the ground switch
14 | Add mufler
15 | 3D print plastic piece for optical enstop | 2023-03-09 | In progress | Will update the 3D files and setting for the 3D print | Kaushik
16 | Check with different Brake Chambers
Docmentations
13 | Pressure safety and Input power safety | 2023-03-11
14 | Upload Documentations and User Manuals | 2023-03-11
15 | BOM and PCB design files | 2023-03-11